## protocol ii
Protocol 5eii (w-z)
|  |  | ii(w) | ii(x) | ii(y) | ii(z)
Project Code | Description | 2024 Projected Additions | Completion Date | % Completion at May 1, 2024 | Estimated Total Project Cost | Cost paid to PNM by Trans Customer or Generator | PNM Comments
65008220 | Sagebrush Station-Transmission | 34908811.02 | 2024-05-01 | 97.47% | 34946464 | No
65009522 | Atrisco Interconnection | 34390787.34 | 2024-07-01 | 90.25% | 34840126 | No
64809420 | Pintado 345kV Switching Station | 32991894.92 | 2024-07-01 | 21% | 35791730.72 | No
64807920 | Prosperity Transmission Substation | 25206741.25 | 2024-12-01 | 64.18% | 28986992 | No
65009024 | Belen PST Substation Install | 24318877.24 | 2024-07-01 | 98.02% | 24564522 | No
65008994 | San Juan Solar | 19094942.19 | 2024-05-01 | 97% | 21672020.57 | Total to be paid by customer $2,424,916.
65009321 | Project Sky Ranch 1 | 17580584.02 | 2024-01-01 | 96% | 53276178.62 | No
65008912 | St Cecilia Station Co2 | 12885416.22 | 2024-11-01 | 65% | 13855316.8 | No
65009321 | Project Sky Ranch 1 | 11537531.94 | 2024-04-01 | 96% | 53276178.62 | No
65009321 | Project Sky Ranch 1 | 8891938.84 | 2024-03-01 | 96% | 53276178.62 | No
64809222 | Trans Relay Replacement 2022 | 6877040.31 | 2024-12-01 | 83% | 21609976.64 | No
65009022 | Belen Phase Shifting Transformer | 6839514.95 | 2024-11-01 | 73.29% | 7116971 | No
65007219 | New Sandia 115 kV Control House | 6223679.82 | 2024-12-01 | 51% | 6829843.72 | No
65007047 | WM 115kV Trans | 5849112.01 | 2024-11-01 | 66% | 6703989.43 | No
64808422 | Embudo Substation | 5559282.88 | 2024-09-01 | 83% | 5659151.54 | No
64807542 | SEL Relay Project Block 1 | 5320078.23 | 2024-12-01 | 0% | 6283164 | No
65009122 | 345kV Structure Repl Phase VI | 5056738.09 | 2024-04-01 | 100% | 30217941.09 | No
64807140 | Tribal Fiber-WFF | 5036617.2 | 2024-04-01 | 100% | 6975776.31 | No
64809222 | Trans Relay Replacement 2022 | 4951192.1 | 2024-09-01 | 83% | 21609976.64 | No
64809222 | Trans Relay Replacement 2022 | 3748888.17 | 2024-08-01 | 83% | 21609976.64 | No
65009321 | Project Sky Ranch 1 | 3352006.68 | 2024-07-01 | 96% | 53276178.62 | No
65007110 | Transmission Blanket | 3180513.64 | N/A | N/A | N/A | No
65009321 | Project Sky Ranch 1 | 3152614.07 | 2024-08-01 | 96% | 53276178.62 | No
64807219 | Ojo Circuit Switcher 02586 | 2252606.67 | 2024-06-01 | 73.69% | 2494070 | No
65007223 | TAG Solar and BESS Project | 2174893.92 | 2024-12-01 | 0% | 2462419.46 | No
65006210 | SW NM Transmission Blanket | 2080507.53 | N/A | N/A | N/A | No
64807222 | WW Reactor Breaker Replacement | 1906515.92 | 2024-12-01 | 0% | 1923232.9 | No
65007710 | Switch Stations Replacements IA | 1580469.23 | 2024-12-01 | N/A | N/A | No
64807025 | Leyendecker Substation | 1558270.84 | 2024-10-01 | 40.23% | 1856757 | No
65008021 | Transm Comm Improvement 2021-2025 | 1547824.46 | 2024-12-01 | 70% | 5131080.59 | No
65009321 | Project Sky Ranch 1 | 1512824.07 | 2024-10-01 | 96% | 53276178.62 | No
64807321 | System Equipment Upgrade-WFF | 1431884.03 | 2024-12-01 | 95% | 2524288.37 | No
65007143 | Asset Health Mntrg-Event Rptg 24-28 | 1333971.72 | 2024-12-01 | 0% | 3387881.11 | No
65009950 | Los Lunas Capacity Expansion Phase4 | 1253495.12 | 2024-09-01 | 10% | 92260145.48 | No