## protocol ii
Protocol 5eii (w-z)
|  |  | ii(w) | ii(x) | ii(y) | ii(z)
Project Code | Description | 2023 Projected Additions | Completion Date | % Completion at May 1, 2023 | Estimated Total Project Cost | Cost paid to PNM by Trans Customer or Generator | PNM Comments
65009321 | Project Sky Ranch 1 | 23857635.03 | 2023-12-01 | 19.56% | 57964928 | None
64807323 | WFF-345kV Struc Repl Phase 5 | 12361686.18 | 2023-12-01 | 100% | 12517021 | None
65009022 | Belen Phase Shifting Transformer | 10256122.01 | 2023-11-01 | 50% | 33039377 | None
64809420 | Pintado 345kV Switching Station | 6514676.41 | 2023-04-01 | 23.37% | 30397474 | None
64807920 | Prosperity Transmission Substation | 6100140.81 | 2023-09-01 | 5.501% | 39877577 | None
65008952 | Intel Expansion - Transmission | 3728214.97 | 2023-04-01 | 80% | 5630481 | None
64807140 | Tribal Fiber-WFF | 3685023.96 | 2023-06-01 | 74.45% | 5970039 | None
64807322 | WFF-Reconfig Tap Sub Unit 2 | 3603065.16 | 2023-12-01 | 99.36% | 8499493 | None
64807540 | NM SEL Relay Project 2021 | 2375900.62 | 2023-08-01 | 76.04% | 6138321 | None
65007710 | Switch Stations Replacements IA | 2023601.94 | 2023-12-01 | 50% | 2526250.01 | None
65008514 | Pachmann Substation-Transmission | 1985860.57 | 2023-07-01 | 28.29% | 11899896 | None
65008514 | Pachmann Substation-Transmission | 1749320.49 | 2023-06-01 | 28.29% | 11899896 | None
65007110 | Transmission Blanket | 1620197.07 | N/A | N/A | N/A | None
65007110 | Transmission Blanket | 1597628.25 | N/A | N/A | N/A | None
65008021 | Transm Comm Improvement 2021-2025 | 1564329.69 | 2023-12-01 | 44.38% | 4900905 | None
64807219 | Ojo Circuit Switcher 02586 | 1545056.78 | 2023-04-01 | 100% | 1590628 | None
65007119 | Asset Health Monitoring_Event Rptg | 1491492.51 | 2023-12-01 | 50% | 1491493 | None
65006110 | ANPP Transmission blanket | 1477684.43 | N/A | N/A | N/A | None
65006210 | SW NM Transmission Blanket | 1463802.07 | N/A | N/A | N/A | None
65007110 | Transmission Blanket | 1279362.62 | N/A | N/A | N/A | None
65009621 | 345kV Structure Repl Phase 4-WFF | 1193392.97 | 2023-04-01 | 100% | 19257219 | None
65008952 | Intel Expansion - Transmission | 1034406.66 | 2023-09-01 | 80% | 5630481 | None