## protocol ii
Protocol 5eii (w-z)
|  |  | ii(w) | ii(x) | ii(y) | ii(z)
Project Code | Description | 2025 Projected Additions | Completion Date | % Completion at May 1, 2025 | Estimated Total Project Cost | Cost paid to PNM by Trans Customer or Generator | PNM Comments
65009950 | Los Lunas Capacity Expansion Phase4 | 83815077.2 | 202510 | 78.65% | 91470657.07 | No
65007223 | TAG Solar and BESS Project | 7226311.12 | 202505 | 99.59% | 8202342.12 | Customer payment of ~$1.5 million | Estimated total project costs have been reduced by the transmission customer payment
65009950 | Los Lunas Capacity Expansion Phase4 | 5977024.68 | 202507 | 78.65% | 91470657.07 | No
65008912 | St Cecilia Station Co2 | 4853468.59 | 202502 | 99.9% | 17791405.62 | No
65007123 | AW 115kV Structure Replace, phase 1 | 3181307.15 | 202512 | 0% | 3181307.15 | No
65009925 | Transmission Line Pole Replcmt 2025 | 2270697.3 | 202512 | 1.717% | 14418536.72 | No
65009321 | Project Sky Ranch 1 | 2204495.17 | 202404 | 100% | 61179358.74 | Customer payment of ~$450k | Estimated total project costs have been reduced by the transmission customer payment
65008912 | St Cecilia Station Co2 | 2176184.8 | 202506 | 99.9% | 17791405.62 | No
64807225 | Failed Sta Equip Replcmt Progm 2025 | 1890107.72 | 202512 | 11.77% | 2511425.9 | No
65007219 | New Sandia 115 kV Control House | 1851281.5 | 202506 | 92.43% | 8673181.27 | No
65008021 | Transm Comm Improvement 2021-2025 | 1779421.62 | 202512 | 87.77% | 5202839.16 | No
65008220 | Sagebrush Station-Transmission | 1518813.6 | 202502 | 98.73% | 36151890.5 | No
64807040 | Norton Capacitor | 1504546.79 | 202507 | 68.26% | 1504546.65 | No
65007143 | Asset Health Mntrg-Event Rptg 24-28 | 1467655.09 | 202512 | 9.325% | 7911530.86 | No
64809222 | Trans Relay Replacement 2022 | 1401549.68 | 202506 | 99.99% | 23828482.75 | No
65007626 | TPL1 Breaker Replacements | 1285920.93 | 202512 | 4.394% | 3190715.86 | No
65008143 | NERC Physical Security 24-28 | 1192077.59 | 202512 | 17.21% | 7592638.37 | No
65007047 | WM 115kV Trans | 1185764.16 | 202508 | 95.76% | 9205268.76 | No
65009950 | Los Lunas Capacity Expansion Phase4 | 1121443.21 | 202512 | 11.77% | 91470657.07 | No
65008220 | Sagebrush Station-Transmission | 1095060.86 | 202504 | 68.26% | 36151890.5 | No
64808422 | Embudo Substation | 1068704.55 | 202503 | 99.95% | 7419745.8 | No
65028040 | FERC 881 - OSI EMS Suite Upgrade | 1010994.45 | 202504 | 84.04% | 1213638.69 | No