## protocol ii
Protocol 5eii (w-z)
|  |  | ii(w) | ii(x) | ii(y) | ii(z)
Project Code | Description | 2026 Projected Additions | Completion Date | % Completion at May 1, 2026 | Estimated Total Project Cost | Cost paid to PNM by Trans Customer or Generator | PNM Comments
65009640 | Mesa del Sol Infrastructure CO2 | 5363103.33 | 2026-11-01 | 0.317% | 107569953.15 | Customer payment of ~$7.5M | Estimated total project costs have been reduced by the transmission customer payment
65009740 | Westpointe Substation-TRN | 4484502.9 | 2026-08-01 | 6.144% | 25047025.69 | No
65009025 | Pajarito to Rio Puerco 345kV Line | 4434005.8 | 2026-09-01 | 0% | 145251627.56 | No
65009025 | Pajarito to Rio Puerco 345kV Line | 4434005.8 | 2026-11-01 | 0% | 145251627.56 | No
65009025 | Pajarito to Rio Puerco 345kV Line | 4434005.8 | 2026-12-01 | 0% | 145251627.56 | No
64809026 | Progress 2 Expansion CO2 | 4398019.29 | 2026-12-01 | 1.538% | 10336532.65 | No
65009740 | Westpointe Substation-TRN | 4299042.34 | 2026-09-01 | 6.144% | 25047025.69 | No
65009740 | Westpointe Substation-TRN | 4260834.93 | 2026-07-01 | 6.144% | 25047025.69 | No
65009926 | Los Lunas Capacity Expansion Phse 5 | 3481246.42 | 2026-07-01 | 7.135% | 147387622.82 | No
65009025 | Pajarito to Rio Puerco 345kV Line | 3440338.77 | 2026-10-01 | 0% | 145251627.56 | No
65009640 | Mesa del Sol Infrastructure CO2 | 3353646.81 | 2026-12-01 | 0.317% | 107569953.15 | Customer payment of ~$7.5M | Estimated total project costs have been reduced by the transmission customer payment
65009740 | Westpointe Substation-TRN | 3179419.93 | 2026-10-01 | 6.144% | 25047025.69 | No
65009640 | Mesa del Sol Infrastructure CO2 | 2985453.78 | 2026-09-01 | 0.317% | 107569953.15 | Customer payment of ~$7.5M | Estimated total project costs have been reduced by the transmission customer payment
65009440 | Sun Lasso Interconnection | 2652471.47 | 2026-12-01 | 0.2597% | 17257153.61 | Customer payment of ~$3.0M | Estimated total project costs have been reduced by the transmission customer payment
65009926 | Los Lunas Capacity Expansion Phse 5 | 2415029.86 | 2026-06-01 | 7.135% | 147387622.82 | No
65009740 | Westpointe Substation-TRN | 2377423.78 | 2026-11-01 | 6.144% | 25047025.69 | No
65007326 | Sunbelt San Juan 345kV Interconnect | 2364679.83 | 2026-11-01 | 2.704% | 4647819.63 | No
65009926 | Los Lunas Capacity Expansion Phse 5 | 2176597.93 | 2026-08-01 | 7.135% | 147387622.82 | No
65009440 | Sun Lasso Interconnection | 1548296.22 | 2026-06-01 | 0.2597% | 17257153.61 | Customer payment of ~$3.0M | Estimated total project costs have been reduced by the transmission customer payment
64807225 | Failed Sta Equip Replcmt Progm 2025 | 1520889.82 | 2026-09-01 | 78.52% | 2784242.27 | No
64807226 | Rodeo Substation Rebuild CO2 | 1478496.09 | 2026-08-01 | 0.03125% | 5120483.75 | No
64807226 | Rodeo Substation Rebuild CO2 | 1475344.93 | 2026-09-01 | 0.03125% | 5120483.75 | No
65009440 | Sun Lasso Interconnection | 1470787.4 | 2026-08-01 | 0.2597% | 17257153.61 | Customer payment of ~$3.0M | Estimated total project costs have been reduced by the transmission customer payment
65009440 | Sun Lasso Interconnection | 1470787.4 | 2026-09-01 | 0.2597% | 17257153.61 | Customer payment of ~$3.0M | Estimated total project costs have been reduced by the transmission customer payment
65009440 | Sun Lasso Interconnection | 1470787.4 | 2026-11-01 | 0.2597% | 17257153.61 | Customer payment of ~$3.0M | Estimated total project costs have been reduced by the transmission customer payment
64809324 | Zia and MD1 Control House Replcmt | 1423175.76 | 2026-06-01 | 31.63% | 6591533.07 | No
64807222 | WW Reactor Breaker Replacement | 1322195.07 | 2026-09-01 | 4.284% | 3093114.71 | No
65009926 | Los Lunas Capacity Expansion Phse 5 | 1249808.16 | 2026-09-01 | 7.135% | 147387622.82 | No
64807626 | YTH Failed Breaker Replacement | 1225840.85 | 2026-07-01 | 3.151% | 5522309.32 | No
65009926 | Los Lunas Capacity Expansion Phse 5 | 1220489.17 | 2026-11-01 | 7.135% | 147387622.82 | No
65009926 | Los Lunas Capacity Expansion Phse 5 | 1220489.17 | 2026-12-01 | 7.135% | 147387622.82 | No
65007110 | Misc. Transmission Blanket | 1199460.02 | N/A | N/A | N/A | No
64807626 | YTH Failed Breaker Replacement | 1181892.9 | 2026-11-01 | 3.151% | 5522309.32 | No
65008826 | Alamogordo Land CO2 | 1102075.2 | 2026-04-01 | 99.51% | 1144597.32 | No
65009424 | Valencia Substation Rebuild - Trans | 1023149.52 | 2026-04-01 | 63.53% | 11410227.28 | No